## Sheet1
Project Goal | Deliverable Name | Predecessor | Time Estimates (In Days) |  |  | Expected Time | Total
|  |  | Optimistic (O) | Normal (M) | Pessimistic (P)
A: Create a Quiz Application | Deliverable 1: User Interface (UI) | E D5 | 0.5 | 1.25 | 2 | 1.2 | 10
| Deliverable 2: External Integration | A D1 | 0.75 | 1.2 | 2 | 1.2
| Deliverable 3: Quiz Application | A D2 | 0.75 | 1.3 | 2 | 1.3
| Deliverable 4: Multiple Question Types | A D3 | 0.75 | 1.3 | 2 | 1.3
| Deliverable 5: Multi-user Functionality | A D4 | 0.75 | 1.3 | 2 | 1.3
| Deliverable 6: Documentation | A D5 | 1 | 1.6 | 2 | 1.5
| Deliverable 7: Temi Integration | A D6 | 0.5 | 1 | 2 | 1
| Deliverable 8: Chocolate Dispenser Integration | A D7 | 0.5 | 1 | 2 | 1
B: Create a Software Development Kit (SDK) for Tour Guides | Deliverable 1: Movement Control | C D4 | 1 | 1.8 | 3 | 1.8 | 15
| Deliverable 2: Pre-programmed Speech | B D1 | 1 | 2 | 3 | 2
| Deliverable 3: Receiving and Interpreting Questions | B D2 | 1 | 2 | 3 | 2
| Deliverable 4: Multimedia Support | B D3 | 1 | 2 | 3 | 2
| Deliverable 5: Application Management | B D4 | 3 | 2.4 | 4 | 2.7
| Deliverable 6: Basic UI Creation | B D5 | 1 | 1.6 | 2 | 1.5
| Deliverable 7: Flexibility for Developers | B D6 | 1 | 1.5 | 2 | 1.5
| Deliverable 8: Documentation | B D7 | 1 | 1.5 | 2 | 1.5
C: Implement Bluetooth Connectivity | Deliverable 1: Research and Planning | F D2 | 1 | 2 | 4 | 2.1 | 10
| Deliverable 2: Development and Integration | C D1 | 2 | 4 | 5 | 3.8
| Deliverable 3: Testing and Validation | C D2 | 1 | 2.5 | 3 | 2.3
| Deliverable 4: Documentation | C D3 | 0.75 | 1.5 | 2 | 1.4
D: Replace Temi's Speech Recognition with ChatGPT | Deliverable 1: Research and Planning | B D8 | 1 | 2 | 4 | 2.1 | 10
| Deliverable 2: Development and Integration | D D1 | 2 | 4 | 5 | 3.8
| Deliverable 3: Testing and Validation | D D2 | 1 | 2.5 | 3 | 2.3
| Deliverable 4: Documentation | D D3 | 0.75 | 1.5 | 2 | 1.4
E: Create a User Guide for Setting Up a PC for Programming Temi | Deliverable 1: Outline User Guide Structure | G D3 | 0.2 | 1 | 2 | 1 | 10
| Deliverable 2: Create Step-by-Step Instructions | E D1 | 2 | 3 | 4 | 3
| Deliverable 3: Design and Formatting | E D2 | 1 | 3 | 4 | 2.8
| Deliverable 4: Testing | E D3 | 1 | 1.5 | 2 | 1.5
| Deliverable 5: Outline User Guide Structure | E D4 | 1 | 1.5 | 2 | 1.5
F: Write a Report/s Necessary for Assessment (Spec and Final) | Deliverable 1: Gather Information | A D | 5 | 6 | 8 | 6.1 | 20
| Deliverable 2: Draft Report/s | A D8 | 7 | 10 | 14 | 10.1
| Deliverable 3: Review and Finalize | F D1 | 2 | 4 | 5 | 3.8
G: Learn Skills Needed to Complete the Project | Deliverable 1: Identify Required Skills | - | 0.7 | 1 | 2 | 1.1 | 5
| Deliverable 2: Research and Acquire Resources | G D1 | 0.5 | 1 | 1.6 | 1
| Deliverable 3: Skill Development | G D2 | 2 | 3 | 3.5 | 2.9